## Sheet1
Schedule Management
Work Breakdown Structure Categories | Start Date | End Date | Responsible | Estimated Hours of a Person |  |  |  |  | Total Working Hours
|  |  |  | Shiva | Sowmya | Anshitha | Vineetha | Swaroopa
1. Initiating | 2020-08-22 | 2020-08-23 | Team | 1.5 | 2.5 | 2 | 2 | 2 | 10
2. Planning | 2020-08-23 | 8/24/2020 | Team | 2.5 | 2 | 2 | 1.5 | 1.5 | 9.5
3. Designing | 2020-08-25 | 11/30/2020 | Team | 2 | 1.5 | 2 | 2.5 | 2 | 10
3.1 UI Design | 2020-08-25 | 9/15/2020 | Shiva | 7 |  |  |  |  | 7
3.2 Synthesis of Design | 2020-09-16 | 2020-10-15 | Team | 1.5 | 2 | 2.5 | 2 | 2.5 | 10.5
3.3 Implementation Iteration | 2020-10-16 | 2020-11-04 | Sowmya |  | 5 |  |  |  | 5
3.4 Early release and Contract finalization | 2020-11-05 | 2020-11-30 | Anshitha |  |  | 6.5 |  |  | 6.5
4. Implementation | 2021-01-20 | 2021-03-30 | Team | 2.5 | 1.5 | 2.5 | 2 | 2 | 10.5
4.1 Application Development | 2021-01-20 | 2021-02-05 | Sowmya |  | 2 |  |  |  | 2
4.2 PWA Implementation | 2021-02-06 | 2021-02-28 | Team | 1.5 | 2 | 1.5 | 2.5 | 2 | 9.5
4.3 Android/iOS Implementation | 2021-03-01 | 2021-03-30 | Vineetha |  |  |  | 5 |  | 5
5. Monitoring and Controlling | 2021-04-03 | 2021-04-17 | Team | 2.5 | 1.5 | 2.5 | 2 | 2.5 | 11
6. Closing | 2021-04-18 | 2021-05-01 | Swaroopa |  |  |  |  | 6 | 6
Total |  |  |  | 21 | 20 | 21.5 | 21.5 | 20.5 | 104.5